## Sheet1
| June | July |  |  |  | August |  |  |  | September |  |  |  | October
| week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4
Feasibility study and requiremnet analysis | bar: week 4
Dataset collection , preprocessing and augmentation | bar: week 1 to week 4
Models and metrics Comparison | bar: week 1 to week 4
HGBRT model training and parameter optimization | bar: week 1 to week 4
Result analysis and Fine tuning | bar: week 1 to week 2
Documentation | bar: week 3 to week 4